## Sheet1
Summary | Issue key | Status | Priority
IOS Screen enhancement-Zoom in Zoom out is | MOB2-30655 | Open | P3 - Major
Autopay-Payment levels mismatch for all product codes | MOB2-30652 | Open | None
Make my payment-Done button is clickable even without giving any amount | MOB2-30650 | Open | P3 - Major
Error message is wrong for Calendar | MOB2-30646 | Open | P3 - Major
Error states - Principal amount(Loan) and Mortgage payment(Mortgage) message is not displayed | MOB2-30644 | Open | P3 - Major
Pay another bill button for Usbank master is Different from Invision | MOB2-30642 | Open | P3 - Major
Make my payment page-decimal is not allowed-IOS | MOB2-30635 | Open | P3 - Major
$NAN is displayed when setup auto pay is selected | MOB2-30542 | In Testing | P3 - Major
Make a payment-'pay$' is showing without space | MOB2-30541 | In Testing | P3 - Major
Dashboard-Billers sorting order is wrong | MOB2-30538 | In Testing | P4 - Minor
Set up auto pay-Before due date-Selection is not working | MOB2-30537 | Development In Progress | P3 - Major
'$' in input field alignment different from invision | MOB2-30536 | Open | P3 - Major
Set up auto pay-radio button is not showing as selected | MOB2-30535 | Open | P3 - Major
Ready to send pop up is large | MOB2-30533 | Open | P3 - Major
Text format is different for card and other billers | MOB2-30532 | Development In Progress | P4 - Minor
Wrong Error message is displayed "Please choose an amount" | MOB2-30531 | In Testing | P3 - Major
Pay button clickable is different ,multiple clicks needed to get into new page | MOB2-30526 | Development In Progress | P3 - Major
Other amount field $0.00 is not getting removed-Automation | MOB2-30417 | Open | P1 - Blocker
Dashboard getting freeze, cant do any activity (hanging problem) | MOB2-30416 | Open | P1 - Blocker
Make a payment - Issues in Make a payment page | MOB2-29608 | Closed | P2 - Critical
Mortgage-Amount is getting added every time done button is selected | MOB2-29604 | Open | P3 - Major
Dashboard-"Next two weeks" label should be displayed | MOB2-29598 | Closed | P3 - Major
Confirmation - Set up autopay button should not have full stop and alignment issue for iOS | MOB2-29595 | Open | P4 - Minor
Set up autopay-Onboarding screen Back button navigation is incorrect | MOB2-29584 | In Testing | P2 - Critical
Dashboard - Bill discovery - Message is not same as in user story | MOB2-29582 | Development In Progress | P3 - Major
Make a payment - Calendar - Dates are not refreshing(Once we choose a date it is reflecting in all product code rather than showing today s date) | MOB2-29580 | Closed | P3 - Major
Set up autopay-Disclaimer message is missing and mismatch | MOB2-29579 | In Testing | P3 - Major
Make a payment - Calendar - While choosing date after the due date, message is displayed on top of the screen | MOB2-29574 | Closed | P3 - Major
Make a payment - Calendar - Able to select dates before current date | MOB2-29573 | Development In Progress | P3 - Major
Make a payment - Calendar - Structure is different from in vision | MOB2-29568 | Development In Progress | P3 - Major
Dashboard - Set up autopay button should not be displayed for mortgage | MOB2-29168 | Closed | P2 - Critical
Dashboard - 'Autopay' text and sync symbol is displayed in different line | MOB2-29167 | Open | P3 - Major
Dashboard-Dismiss button is showing for internal billers | MOB2-29166 | Closed | P2 - Critical
Dashboard - Orange color card should not come for overdue and today billers | MOB2-29164 | Closed | P2 - Critical
Dashboard - 'Set up autopay' button is not displayed as in invision | MOB2-29161 | In Testing | P4 - Minor
Review and Edit - Header is overlapped with Account type | MOB2-28810 | Closed | P3 - Major
Review and edit page-Error message displaying incorrectly | MOB2-28786 | Closed | P3 - Major
Payment level page-Back button redirecting to Dashboard page | MOB2-28783 | Closed | P3 - Major
Auto pay-Make my payment field accepting "0" days | MOB2-28780 | Closed | P3 - Major
Review and edit page-Amount selection display errors | MOB2-28777 | Closed | P3 - Major
Review and edit page-Calender component errors | MOB2-28775 | Development In Progress | P3 - Major
Payment level page-payment levels are not displayed | MOB2-28774 | Closed | P3 - Major
Confirmation - Disclaimer should come above 'pay another bill' button and heading mismatch with invision | MOB2-28738 | Closed | P4 - Minor
Disclaimer is missing content in multiple screens | MOB2-28737 | Closed | P4 - Minor
Dashboard -Billers are not sorted in alphabetical order | MOB2-28736 | In Testing | P4 - Minor
Payment level - Save button is missing for 3 Biller | MOB2-28735 | Closed | P2 - Critical
Pay from-Choose the account header is displayed instead of select the account | MOB2-28734 | Closed | P4 - Minor
Dashboard - Due date is displayed in wrong format under This week | MOB2-28732 | Closed | P3 - Major
Choose amount-Deposit account 2 is click able but not select able | MOB2-28680 | Closed | P3 - Major
Payment level-Continue CTA is displayed instead of Save CTA | MOB2-28679 | Closed | P4 - Minor
Add a bill button should be in Blue color | MOB2-28678 | Closed | P3 - Major
Review and edit payment-Incorrect header for make a selection | MOB2-28677 | Closed | P3 - Major
Review and edit - Message is coming below review and edit heading | MOB2-28676 | Closed | P3 - Major
Dashboard page-Pay bills not displaying when redirected from quick action menu | MOB2-28520 | Closed | P1 - Blocker
Mortgage Payment level - All input fields are accepting $0.00 for payment | MOB2-28183 | Closed | P3 - Major
Review and edit payment - Payment amount is displayed as $NaN | MOB2-28178 | Open | P3 - Major
Payment level - Getting error while choosing past due and mortgage only | MOB2-28175 | Closed | P3 - Major
Payment level - $5.21 is showing by default in input field under late fees | MOB2-28171 | Closed | P3 - Major
Mortgage payment level- $0.00 is not removing in input field | MOB2-28167 | Open | P3 - Major
Mortgage Payment level - Input field limit should not be more than 16+2 for additional principal, late fees, additional escrow | MOB2-28166 | Open | P2 - Critical
Mortgage Payment level - Checkbox is displayed with blue outline | MOB2-28165 | Closed | P4 - Minor
Payment level-Characters more than two are accepting after decimal value | MOB2-27892 | Open | P3 - Major
Payment level-Extra digit getting added in other amount field | MOB2-27891 | Open | P3 - Major
Payment level - Arrow head in 'amount level defined and amount due defined' is in wrong color | MOB2-27889 | Closed | P4 - Minor
Payment level -Payment amount same in other amount field | MOB2-27888 | Closed | P3 - Major
Dashboard page-Incorrect due date format and improper sorting | MOB2-27803 | Closed | P3 - Major
Dashboard page-Due date is in wrong format in This week | MOB2-27708 | Closed | P3 - Major
Choose from account-Radio button is not clickable for deposit account | MOB2-27350 | Closed | P3 - Major
Review & edit payment - Disclaimer message error | MOB2-27345 | Closed | P4 - Minor
Ready to send - Background scroll is working and able to switch to 'review & edit payment' | MOB2-27334 | Closed | P3 - Major
Payment level - Button missing in green alert message | MOB2-27330 | Closed | P3 - Major
Choose Payment - Alphanumeric keyboard is displayed instead of Number pad | MOB2-27328 | On Hold | P2 - Critical
Choose payment - Digits not visible in other amount input field | MOB2-27131 | In Testing | P3 - Major
Confirmation - Alignment issue in confirmation page | MOB2-26896 | On Hold | P4 - Minor
Dashboard - "Due month" format should be displayed under This month | MOB2-26895 | Closed | P4 - Minor
Choose payment,Review & edit payment - Text message Errors | MOB2-26894 | Closed | P4 - Minor
Choose payment - Issues in "input field" under choose payment screen | MOB2-26893 | Closed | P2 - Critical
Dashboard,Payment level- Texts in multiple screens have multiple upper case letters | MOB2-26892 | Closed | P4 - Minor
Choose payment - Hover Effect should not be there for radio button | MOB2-26891 | Closed | P4 - Minor
Choose Pay from account - Arrow head is missing | MOB2-26890 | Closed | P4 - Minor
Choose payment screen - "Done" button is missing in number pad | MOB2-26887 | On Hold | P3 - Major

## Sheet2
Summary | Issue key | Status | Priority | Comments | Owner
IOS Screen enhancement-Zoom in Zoom out is | MOB2-30655 | Open | P3 - Major |  | Mani
Autopay-Payment levels mismatch for all product codes | MOB2-30652 | Open | None |  | Sateesh
Make my payment-Done button is clickable even without giving any amount | MOB2-30650 | Open | P3 - Major | Shield Issues
Error message is wrong for Calendar | MOB2-30646 | Open | P3 - Major |  | Niranjan
Error states - Principal amount(Loan) and Mortgage payment(Mortgage) message is not displayed | MOB2-30644 | Open | P3 - Major |  | Dinesh/Santhosh
Pay another bill button for Usbank master is Different from Invision | MOB2-30642 | Open | P3 - Major |  | Sateesh
Make my payment page-decimal is not allowed-IOS | MOB2-30635 | Open | P3 - Major | Shield Issues
Set up auto pay-Before due date-Selection is not working | MOB2-30537 | Development In Progress | P3 - Major | Fixed
'$' in input field alignment different from invision | MOB2-30536 | Open | P3 - Major | Fixed
Set up auto pay-radio button is not showing as selected | MOB2-30535 | Open | P3 - Major | Shield Issues
Ready to send pop up is large | MOB2-30533 | Open | P3 - Major | Shield Issues
Text format is different for card and other billers | MOB2-30532 | Development In Progress | P4 - Minor | Fixed
Pay button clickable is different ,multiple clicks needed to get into new page | MOB2-30526 | Development In Progress | P3 - Major | Fixed
Other amount field $0.00 is not getting removed-Automation | MOB2-30417 | Open | P1 - Blocker | Shield Issues
Dashboard getting freeze, cant do any activity (hanging problem) | MOB2-30416 | Open | P1 - Blocker | Shield Issues
Mortgage-Amount is getting added every time done button is selected | MOB2-29604 | Open | P3 - Major |  | Dinesh/Santhosh
Confirmation - Set up autopay button should not have full stop and alignment issue for iOS | MOB2-29595 | Open | P4 - Minor |  | Sateesh
Dashboard - Bill discovery - Message is not same as in user story | MOB2-29582 | Development In Progress | P3 - Major | mock data issue
Make a payment - Calendar - Able to select dates before current date | MOB2-29573 | Development In Progress | P3 - Major | Shield Issues
Make a payment - Calendar - Structure is different from in vision | MOB2-29568 | Development In Progress | P3 - Major | Shield Issues
Dashboard - 'Autopay' text and sync symbol is displayed in different line | MOB2-29167 | Open | P3 - Major | Hold
Review and edit page-Calender component errors | MOB2-28775 | Development In Progress | P3 - Major | Shield Issues
Review and edit payment - Payment amount is displayed as $NaN | MOB2-28178 | Open | P3 - Major |  | Dinesh/Santhosh
Mortgage payment level- $0.00 is not removing in input field | MOB2-28167 | Open | P3 - Major |  | Dinesh/Santhosh
Mortgage Payment level - Input field limit should not be more than 16+2 for additional principal, late fees, additional escrow | MOB2-28166 | Open | P2 - Critical |  | Dinesh/Santhosh
Payment level-Characters more than two are accepting after decimal value | MOB2-27892 | Open | P3 - Major | Shield Issues
Payment level-Extra digit getting added in other amount field | MOB2-27891 | Open | P3 - Major |  | Sateesh
Choose Payment - Alphanumeric keyboard is displayed instead of Number pad | MOB2-27328 | On Hold | P2 - Critical
Confirmation - Alignment issue in confirmation page | MOB2-26896 | On Hold | P4 - Minor
Choose payment screen - "Done" button is missing in number pad | MOB2-26887 | On Hold | P3 - Major

## Summary
P1 |  |  | P2 |  |  |  | P3 |  |  | P4
Open | Dev In-Progress | In-Testing | Open | Closed | Dev In-Progress | In-Testing | Open | Dev In-Progress | In-Testing | Open | Dev In-Progress | In-Testing
2 | 1 |  | 2 |  | 2 |  | 16 | 6 |  | 3 | 1
total 30 defects :
5 | fixed
10 | Shield Issues - Expecting 6 to be closed once Modal, Check box, Radio and Calendar is published.
4 | On Hold - need validation from BA
11 open defects - 6 with Dinesh for Mortgage, 4 with sateesh, 1 with Niranjan