## EPIC
Release | EPIC # | EPIC | Status
First Pilot – April | MOB2-22163 | •Select Biller Dashboard [MOB2-22163] | RAG
First Pilot – April | MOB2-17724 | •Internal Payment to credit cards [MOB2-17724]
First Pilot – April | MOB2-17727 | •Internal Payment to Loan [MOB2-17727]
First Pilot – April | MOB2-17726 | •Internal Payment to LOC [MOB2-17726]
First Pilot – April | MOB2-17728 | •Internal Payment to Lease [MOB2-17728]
First Pilot – April | MOB2-23011 | •Future dated payment to Credit Cards [MOB2-23011]

## Story
EPIC # | Story # | Team | Story Description | Status | type | Visual Design | Story Grooming | Component Identfied | Components | Comp. Readiness | Contract (JSON) | Mock Service | Service EndPoints | Dev. complete Target | Integration Sprint | Testing Sprint
MOB2-22163 | MOB2-30927 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Dashboard ¦ - List view (Part 1) |  | Business Story | Yes | Yes | Yes | Cards, List | In Progress | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
MOB2-22163 | MOB2-31975 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Dashboard ¦ - List view (Part 2) |  | Business Story | Yes | Yes | Yes | Cards, List | In Progress | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
MOB2-17727 | MOB2-30929 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Bill Details Screen - Part 1 |  | Business Story | Yes | Yes | Yes | Modal, List | In Progress | Yes | Yes | In progress | Sprint-3 | Sprint-3 | Sprint-3
MOB2-17726 | MOB2-31984 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Bill Details Screen - Part 2 |  | Business Story | Yes | Yes | Yes | Modal, List | In Progress | Yes | Yes | In progress | Sprint-3 | Sprint-3 | Sprint-3
MOB2-17728 | MOB2-30930 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Review Details - Part 1 |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
MOB2-23011 | MOB2-,32016 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Review Details - Part 2 |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2- 32026 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦ Review Details - Part 3 |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-30933 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Choose Amount - Part 1 |  | Business Story | Yes | Yes | Yes | Input, Radio, Checkbox | In Progress | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-, 31977 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Choose Amount - Part 2 |  | Business Story | Yes | Yes | Yes | Input, Radio, Checkbox | In Progress | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-30934 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Change delivery date - Part -1 |  | Business Story | Yes | Yes | Yes | calendar | Completed | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-, 32007 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Change delivery date - Part -2 |  | Business Story | Yes | Yes | Yes | calendar | Completed | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-#31648 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Shield Component |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-31093 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Confirmation |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-31151 | UI Dev | Mortgage A/c Suppressed & Filter for CCD/BCD/EXL for future date Part - 1 |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-31157 | UI Dev | Mortgage A/c Suppressed & Filter for CCD/BCD/EXL for future date Part - 2 |  | Business Story | Yes | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-31172 | UI Dev | TUX Integration |  | Tech Story | NA | Yes |  |  |  | NA | NA | NA | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-30935 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Select the Account |  | Business Story | Yes | Yes | Yes | Radio | In Progress | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-31618 | UI Dev | Bill Pay - App ¦ One-time & Scheduled Payment ¦Ready to Send |  | Business Story | Yes | Yes | Yes | Modal | In Progress | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-28366 | UI Dev | Bill Pay - App ¦ AEM Integration CCD Payment |  | Tech Story | NA | In Progress |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4
| MOB2-28368 | UI Dev | Bill Pay - App ¦ AEM Integration Internal Payment |  | Tech Story | NA | In Progress |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4
| TBD | UI Dev | Bill Pay - App ¦ AEM Integration |  | Tech Story | NA | In Progress |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4
| TBD | UI Dev | Bill Pay - App ¦ AEM Integration |  | Tech Story | NA | In Progress |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4
| TBD | UI Dev | Bill Pay - App ¦ AEM Integration |  | Tech Story | NA | In Progress |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4
| MOB2-31624 | UI Dev | Bill Pay - App ¦ API Error Code Implementation |  | Tech Story | NA | Yes |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4
| MOB2-28771 | UI Dev | Kill switch Implementation |  | Tech Story | NA | Yes |  |  |  | Yes | NA | Yes | Sprint-3 | Sprint-3 | Sprint-3
| MOB2-31620 | UI Dev | Bill Pay - App ¦ Copy deck updates |  | Tech Story | NA | Yes |  |  |  | Yes | NA | Yes | Sprint-4 | Sprint-4 | Sprint-4