## Team defects ready for testing
Issue key | Summary | Status | Priority | Created | Updated | status | author of defect
MOB2-29608 | Make a payment - Issues in Make a payment page | Development In Progress | P2 - Critical | 2020-01-09 06:09 | 2020-01-17 01:40 | Fixed | Sateesh
MOB2-29604 | Mortgage-Amount is getting added every time done button is selected | Open | P3 - Major | 2020-01-09 06:01 | 2020-01-17 00:58 | In Progress | Dinesh | Checkbox issue with shield components
MOB2-29598 | Dashboard-"Next two weeks" label should be displayed | In Testing | P3 - Major | 2020-01-09 05:42 | 2020-01-17 06:46 | In Testing | Santhosh
MOB2-29595 | Confirmation - Set up autopay button should not have full stop and alignment issue for iOS | Open | P4 - Minor | 2020-01-09 05:36 | 2020-01-17 07:42
MOB2-29584 | Set up autopay-Onboarding screen Back button navigation is incorrect | Development In Progress | P2 - Critical | 2020-01-09 05:25 | 2020-01-17 03:21
MOB2-29582 | Dashboard - Bill discovery - Message is not same as in user story | Development In Progress | P3 - Major | 2020-01-09 05:07 | 2020-01-17 01:17 | Fixed | Santhosh
MOB2-29580 | Make a payment - Calendar - Dates are not refreshing(Once we choose a date it is reflecting in all product code rather than showing today s date) | Open | P3 - Major | 2020-01-09 04:59 | 2020-01-17 00:59 | Fixed | Niranjan
MOB2-29579 | Set up autopay-Disclaimer message is missing and mismatch | Open | P3 - Major | 2020-01-09 04:56 | 2020-01-17 06:45 | Fixed | Sateesh
MOB2-29576 | Set up autopay-Confirmation page mismatch from invision | Open | P3 - Major | 2020-01-09 04:33 | 2020-01-17 00:59 | fixed | Sateesh
MOB2-29575 | Set up autopay-Make my payments-1 'days' before due date is coming | In Testing | P4 - Minor | 2020-01-09 04:31 | 2020-01-17 06:55 | In Testing | Sateesh
MOB2-29574 | Make a payment - Calendar - While choosing date after the due date, message is displayed on top of the screen | Open | P3 - Major | 2020-01-09 04:04 | 2020-01-17 01:00 | Fixed | Niranjan
MOB2-29573 | Make a payment - Calendar - Able to select dates before current date | Open | P3 - Major | 2020-01-09 03:58 | 2020-01-19 23:05 | Shield Issues | Niranjan
MOB2-29568 | Make a payment - Calendar - Structure is different from in vision | Open | P3 - Major | 2020-01-09 03:35 | 2020-01-19 23:04 | Shield Issues | Niranjan
MOB2-29168 | Dashboard - Set up autopay button should not be displayed for mortgage | In Testing | P2 - Critical | 2020-01-06 04:42 | 2020-01-17 07:14 | Fixed | Sateesh
MOB2-29167 | Dashboard - 'Autopay' text and sync symbol is displayed in different line | Open | P3 - Major | 2020-01-06 04:39 | 2020-01-06 04:47 | Hold | Santhosh
MOB2-29166 | Dashboard-Dismiss button is showing for internal billers | Open | P2 - Critical | 2020-01-06 04:28 | 2020-01-07 00:14 | Fixed | Santhosh
MOB2-29164 | Dashboard - Orange color card should not come for overdue and today billers | In Testing | P2 - Critical | 2020-01-06 04:18 | 2020-01-17 07:15 | In Testing | Santhosh
MOB2-29161 | Dashboard - 'Set up autopay' button is not displayed as in invision | In Testing | P4 - Minor | 2020-01-06 04:10 | 2020-01-08 00:56 | In Testing | Santhosh
MOB2-28810 | Review and Edit - Header is overlapped with Account type | Open | P3 - Major | 2019-12-27 02:01 | 2020-01-10 03:44 | requirement changed | Sateesh
MOB2-28786 | Review and edit page-Error message displaying incorrectly | In Testing | P3 - Major | 2019-12-26 06:44 | 2020-01-17 07:21 | requirement changed | Sateesh
MOB2-28783 | Payment level page-Back button redirecting to Dashboard page | Development In Progress | P3 - Major | 2019-12-26 05:49 | 2020-01-17 08:10 | requirement changed | Sateesh
MOB2-28780 | Auto pay-Make my payment field accepting "0" days | In Testing | P3 - Major | 2019-12-26 05:24 | 2020-01-10 03:46 | Fixed | Niranjan
MOB2-28777 | Review and edit page-Amount selection display errors | Open | P3 - Major | 2019-12-26 04:26 | 2020-01-10 03:47 | requirement changed | Sateesh
MOB2-28775 | Review and edit page-Calender component errors | Development In Progress | P3 - Major | 2019-12-26 04:16 | 2020-01-06 06:43 | paritally fixed, for icon shield needs to be updated | Sateesh
MOB2-28774 | Payment level page-payment levels are not displayed | Development In Progress | P3 - Major | 2019-12-26 03:59 | 2020-01-07 23:15 | requirement changed | Sateesh
MOB2-28738 | Confirmation - Disclaimer should come above 'pay another bill' button and heading mismatch with invision | Closed | P4 - Minor | 2019-12-24 08:41 | 2020-01-06 07:45
MOB2-28737 | Disclaimer is missing content in multiple screens | Development In Progress | P4 - Minor | 2019-12-24 08:38 | 2020-01-10 09:32 | requirement changed | Sateesh
MOB2-28736 | Dashboard -Billers are not sorted in alphabetical order | Development In Progress | P4 - Minor | 2019-12-24 08:31 | 2020-01-06 06:44 | Yet to fix | Santhosh
MOB2-28735 | Payment level - Save button is missing for 3 Biller | Closed | P2 - Critical | 2019-12-24 08:19 | 2020-01-02 07:22
MOB2-28734 | Pay from-Choose the account header is displayed instead of select the account | Development In Progress | P4 - Minor | 2019-12-24 08:18 | 2019-12-26 02:48 | requirement changed | Sateesh
MOB2-28732 | Dashboard - Due date is displayed in wrong format under This week | Closed | P3 - Major | 2019-12-24 08:12 | 2020-01-02 07:23
MOB2-28680 | Choose amount-Deposit account 2 is click able but not select able | Development In Progress | P3 - Major | 2019-12-23 09:10 | 2020-01-08 01:42
MOB2-28679 | Payment level-Continue CTA is displayed instead of Save CTA | Closed | P4 - Minor | 2019-12-23 08:48 | 2020-01-02 07:23
MOB2-28678 | Add a bill button should be in Blue color | Closed | P3 - Major | 2019-12-23 08:48 | 2020-01-06 07:45
MOB2-28677 | Review and edit payment-Incorrect header for make a selection | Closed | P3 - Major | 2019-12-23 08:34 | 2020-01-02 07:25
MOB2-28676 | Review and edit - Message is coming below review and edit heading | Closed | P3 - Major | 2019-12-23 08:24 | 2020-01-02 07:26
MOB2-28520 | Dashboard page-Pay bills not displaying when redirected from quick action menu | Closed | P1 - Blocker | 2019-12-18 00:45 | 2020-01-02 07:32
MOB2-28183 | Mortgage Payment level - All input fields are accepting $0.00 for payment | Closed | P3 - Major | 2019-12-12 05:03 | 2020-01-02 07:26
MOB2-28178 | Review and edit payment - Payment amount is displayed as $NaN | Development In Progress | P3 - Major | 2019-12-12 04:28 | 2020-01-07 00:37 | requirement changed | Sateesh
MOB2-28175 | Payment level - Getting error while choosing past due and mortgage only | Closed | P3 - Major | 2019-12-12 04:21 | 2019-12-18 01:57
MOB2-28171 | Payment level - $5.21 is showing by default in input field under late fees | Closed | P3 - Major | 2019-12-12 04:13 | 2019-12-18 01:56
MOB2-28167 | Mortgage payment level- $0.00 is not removing in input field | Open | P3 - Major | 2019-12-12 04:00 | 2020-01-17 07:55
MOB2-28166 | Mortgage Payment level - Input field limit should not be more than 16+2 for additional principal, late fees, additional escrow | Development In Progress | P2 - Critical | 2019-12-12 03:57 | 2020-01-10 09:31
MOB2-28165 | Mortgage Payment level - Checkbox is displayed with blue outline | Closed | P4 - Minor | 2019-12-12 03:35 | 2019-12-18 01:58
MOB2-27892 | Payment level-Characters more than two are accepting after decimal value | Open | P3 - Major | 2019-12-11 01:52 | 2019-12-27 04:40
MOB2-27891 | Payment level-Extra digit getting added in other amount field | Open | P3 - Major | 2019-12-11 01:02 | 2019-12-27 06:27
MOB2-27889 | Payment level - Arrow head in 'amount level defined and amount due defined' is in wrong color | Development In Progress | P4 - Minor | 2019-12-11 00:32 | 2020-01-10 09:31 | requirement changed | Sateesh
MOB2-27888 | Payment level -Payment amount same in other amount field | Closed | P3 - Major | 2019-12-11 00:32 | 2019-12-18 06:03
MOB2-27803 | Dashboard page-Incorrect due date format and improper sorting | Closed | P3 - Major | 2019-12-10 05:16 | 2019-12-18 01:54
MOB2-27708 | Dashboard page-Due date is in wrong format in This week | Closed | P3 - Major | 2019-12-09 03:56 | 2019-12-18 01:53
MOB2-27350 | Choose from account-Radio button is not clickable for deposit account | Closed | P3 - Major | 2019-12-04 06:29 | 2019-12-18 01:53
MOB2-27345 | Review & edit payment - Disclaimer message error | Open | P4 - Minor | 2019-12-04 05:10 | 2020-01-10 09:30 | Fixed | Sateesh
MOB2-27334 | Ready to send - Background scroll is working and able to switch to 'review & edit payment' | On Hold | P3 - Major | 2019-12-04 04:26 | 2020-01-10 06:39
MOB2-27330 | Payment level - Button missing in green alert message | On Hold | P3 - Major | 2019-12-04 03:51 | 2020-01-10 07:06
MOB2-27328 | Choose Payment - Alphanumeric keyboard is displayed instead of Number pad | On Hold | P2 - Critical | 2019-12-04 03:22 | 2019-12-20 05:35
MOB2-27131 | Choose payment - Digits not visible in other amount input field | On Hold | P3 - Major | 2019-11-29 08:32 | 2019-12-23 10:26
MOB2-26896 | Confirmation - Alignment issue in confirmation page | On Hold | P4 - Minor | 2019-11-27 09:06 | 2020-01-10 06:37
MOB2-26895 | Dashboard - "Due month" format should be displayed under This month | Closed | P4 - Minor | 2019-11-27 08:56 | 2019-12-11 06:15
MOB2-26894 | Choose payment,Review & edit payment - Text message Errors | Closed | P4 - Minor | 2019-11-27 08:50 | 2019-12-11 06:15
MOB2-26893 | Choose payment - Issues in "input field" under choose payment screen | Closed | P2 - Critical | 2019-11-27 08:35 | 2019-12-11 06:15
MOB2-26892 | Dashboard,Payment level- Texts in multiple screens have multiple upper case letters | Closed | P4 - Minor | 2019-11-27 08:31 | 2020-01-02 07:28
MOB2-26891 | Choose payment - Hover Effect should not be there for radio button | Closed | P4 - Minor | 2019-11-27 08:23 | 2019-12-18 01:57
MOB2-26890 | Choose Pay from account - Arrow head is missing | Closed | P4 - Minor | 2019-11-27 08:16 | 2019-12-11 06:16
MOB2-26887 | Choose payment screen - "Done" button is missing in number pad | On Hold | P3 - Major | 2019-11-27 07:59 | 2019-12-20 05:36
MOB2-26886 | Choose payment - Back button in payment detail page is misaligned | Closed | P4 - Minor | 2019-11-27 07:51 | 2019-12-12 06:08
MOB2-26884 | App Crashing in Android Lower Version such as 7.0 | Closed | P1 - Blocker | 2019-11-27 07:28 | 2019-12-18 06:04
MOB2-26883 | Choose payment - Payment levels missing in US bank visa 4121 | Closed | P3 - Major | 2019-11-27 07:22 | 2019-12-18 01:52
MOB2-26882 | Dashboard - Header in dashboard is displayed as "Pay a bill" instead of Pay bills | Closed | P3 - Major | 2019-11-27 07:15 | 2020-01-02 07:28
MOB2-30327 | Mortgage Payment Levels Selection Issues | Open | P1 - Blocker