## Sheet1
Screen Name | New features/Changes | Scope | Comments | Task | DEV Effort(Product Codes Suppport) | Accessibility | Internationalization | JEST/Lint/Pixel Perfect | Total
Dashboard | Static Layout changed - List view UI Change: 1) Remove expand/collapase from LIST Item 2) Layout/Navigation/Code refactor revision | Pilot | Type of cards allowed like blue, red, orange, yellow? Need to disucss with shield and UX team on how to display bills if more like 100+ for each section | 1) Layout Design - 24h 2) Code Refactor for expand collapse functionality and remove unused scss - 4h 3) Refactor payment level and own account list API calls - 6h 4) navigations and ID attributes for QA auto mation -4h | 38 | 4 | 2 | 30 | 74
| View/Dismiss bill | Awaiting Clarification
| Calendar view | Out of scope for pilot
| Add bill | Out of scope for pilot
| Native Side header change | Pilot |  | 1) header design and ID attributes for QA auto mation - 4h | 4 | 1 | 1 | 3 | 9
Bill Details | Whole new screen 1) Conditional Sub header 2) Take Control section 3) Past payment & View all history Including service Integration | Pilot | View all history new screen/or data refresh | 1) new page/container/component creations and static layout design - 24h 2) condtional sub header - 4h 3) current bill implematations - 8h 4) Take control section implementations - 6h 5) past payment implementations and API integration - 16h 6) Button Navigations and ID attributes for QA automation -4h | 58 | 4 | 2 | 44 | 108
| Auto pay | Awaiting Clarification
| Alerts | Out of scope for pilot
| Digital bills | Out of scope for pilot
| Learn more | Awaiting Clarification
| View All history | Awaiting Clarification
Review Details | Whole flow change 1) Card to List view 2) Choose Amount page 3) Change Delivery data page 4) pay from Account page 5) Layout revision 6) Functional changes for validations | Pilot |  | 1) Code Refactor - 16h 2) Layout re-design and card to list view- 24h 3) create new pages/containers for choose amount , change delivery date and payfrom account- 16h 4) Page validations, Error/ success/Info notifications implmentations - 24h 4) Button navigations and ID attributes for QA automation -4h | 84 | 10 | 5 | 64 | 163
| Choose Amount new screen design, Same validaitons | Pilot |  | 1) code refactor - 4h 2) new screen design for all product codes - 20h 3) Payment list new validations - 32h 4) Button navigations and ID attributes for QA auto mation -4h | 60 | 4 | 2 | 48 | 114
| Calendar new screen (UX changes), Same validations | Pilot |  | 1) code refactor - 4h 2) new screen design for all product codes - 24h 3) one time and scheduler payment validations for calender - 16h 4) Button navigations and ID attributes for QA auto mation -4h | 48 | 4 | 2 | 36 | 90
| Pay from Account new screen (UX changes), Same validations | Pilot |  | 1) code refactor - 4h 2) new screen design - 8h 3) caf flag 1 & 3 validations for from accounts - 4h 4) Button navigations and ID attributes for QA automation -4h | 20 | 2 | 2 | 16 | 40
| Add external account | Out of scope for pilot | Hide option
Ready To send & All Screens | Product code wise messages | Pilot | is it CMS driven?(like disclaimer) | 1) code refactor - 4h 2) Product code wise messages and design - 16h 3) Button navigations and ID attributes for QA automation -4h | 24 | 4 | 2 | 17 | 47
Confirmation | Simple UX changes | Pilot |  | 1) new UI design changes - 12h 2) Button navigations and ID attributes for QA automation -4h | 16 | 4 | 2 | 11 | 33
Shield | LIST with Infinite Scroll | Pilot
| Enhance Calendar with UX changes | Pilot
| UX changes for Radio, Checkbox | Pilot
| Input | Pilot
Common Activities with Redesign | Site Cat Integration | Pilot
| API Error Codes Implementation | Pilot |  | 1) Dashboard API error validations - 8h 2) Choose Amount page API error validations - 2h 3) Pay from Account API error validations - 2h 4) Change Delivery date API error validations - 2h 5) Change Delivery date API error validations - 2h | 18 | 4 | 2 | 14 | 38
| AEM/CMS Integration | Pilot |  | AEM/CMS Integration for Dashboard ,Bill Details, Choose Amount page, Pay from Account , Change Delivery date, confirmation, review detail screen - 28h | 28 | 4 | 2 | 12 | 46
Spinner, Modal, LIST
gif need to be updated
| Infinite Scroll for LIST | Bad experience
We need to implement on our Old List
Our Old List vs DIY List