## Sheet1
MOB2-34194 | Add biller Via Search
Creating new files for components , container, saga, actions, services, selecters, reducer | 12h
Add a bill via search static prototype | 18h
Auto complete component creation | 12h
Generate biller list onload, change biller list based on dropdown change | 16h
auto complete functionliaty and service integration | 20h
Display popup for already exist biller | 8h
Add a bill form Field validations | 14h
Creating new files for Add bill saga, actions, services, selecters, reducer | 8h
Add a bill post call related functionality and validations | 6h
Jest Test cases | 32h
Accessbility | 4h
Internalization | 4h
ID attributes and navigation | 4h
Pixel perfect | 4h
Dependency with shiled dropdown and data-list
Dependency with mock json
MOB2-34195 | Add biller manually
Creating new files for components , container, saga, actions, services, selecters, reducer | 12h
Add a bill via manually static prototype and ID attributes | 8h
address component creation and integration
Add a bill form Field validations | 12h
Add a bill post call related functionality and validations | 4h
Jest Test cases | 20h
Accessbility | 4h
Internalization | 4h
Pixel perfect | 4h
Dependency with shiled dropdown and data-list
Dependency with mock json
MOB2-34196 | Edit& Delete biller ( via Search)
Creating new saga, actions, services, selecters, reducer for fetching edit information | 12h
Creating new actions, services for update information | 4h
Creating new actions, services for delete information | 4h
Jest Test cases | 16h
MOB2-34197 | Edit& Delete biller ( via manuall added)
Creating new saga, actions, services, selecters, reducer for fetching edit information | 12h
Creating new actions, services for update information | 4h
Creating new actions, services for delete information | 4h
Jest Test cases | 16h